Project Management Essentials

Topic-Level Outline

Days:	1

Prerequisites:	None

Unit 1:	Defining the project

Topic A: 0	Project participants

A-1:	Determining influence of stakeholders

Topic B: 0	Project objectives and planning

B-1:	Identifying benefits of project planning

B-2:	Prioritizing constraints in a project

Unit 2:	Activities and dependencies

Topic A: 0	Project activities

A-1:	Creating a WBS

A-2:	Identifying types of project activities

A-3:	Creating PERT charts

Topic B: 0	Activity analysis

B-1:	Determining appropriate level of detail

B-2:	Creating activity analysis forms

B-3:	Assigning work

Topic C: 0	Activity estimation

C-1:	Estimating project activities

C-2:	Identifying problems and opportunities

Topic D: 0	Dependencies

D-1:	Identifying dependencies

D-2:	Identifying lags and slack

Unit 3:	Project scheduling

Topic A: 0	Schedule development

A-1:	Identifying benefits and constraints

A-2:	Identifying mathematical techniques for analysis

A-3:	Understanding network diagrams

A-4:	Identifying arrow charting methods

A-5:	Creating Gantt charts

Topic B: 0	CPM and PERT

B-1:	Understanding critical path

B-2:	Understanding CPM scheduling and calculations

B-3:	Understanding duration compression

B-4:	Calculating float

Unit 4:	Project change control

Topic A: 0	Project change control system

A-1:	Understanding project change control system

Topic B: 0	Controlling change

B-1:	Accommodating change

B-2:	Understanding project change control board

Unit 5:	Financial issues

Topic A: 0	Fundamentals of cost estimating

A-1:	Analyzing historical information

A-2:	Understanding activity duration and cost estimates

A-3:	Identifying problems while estimating costs

Topic B: 0	Organizational financial systems

B-1:	Understanding organizational financial issues

B-2:	Budgeting factors

Unit 6:	Project performance

Topic A: 0	Measuring project performance

A-1:	Determining project performance

A-2:	Using calculations in earned value analysis

A-3:	Controlling project cost

Topic B: 0	Reporting project performance

B-1:	Understanding performance reports

B-2:	Understanding status reports

B-3:	Understanding progress reports

B-4:	Closing projects

B-5:	Understanding final project report