Project 2003:
Advanced

Topic-Level Outline

Days:	1

Prerequisites:	Project 2003: Basic or equivalent experience

Unit 1:	Tracking project work

Topic A: 0	Managing a project

A-1:	Saving a baseline plan

Topic B: 0	Updating the progress of tasks

B-1:	Updating the percent complete of a task

B-2:	Updating actual start and finish dates

B-3:	Updating tasks that are in progress

B-4:	Updating the actual work performed on a task

B-5:	Saving an interim plan

Topic C: 0	Observing project progress

C-1:	Displaying the Earned Value table

C-2:	Viewing progress in Network Diagram view

Unit 2:	Analyzing and adjusting the plan

Topic A: 0	Analyzing the plan

A-1:	Viewing project statistics

A-2:	Displaying slippage and slack in a plan

Topic B: 0	Rescheduling tasks

B-1:	Splitting a task

B-2:	Delaying resource work

B-3:	Assigning overtime

Unit 3:	Formatting and reporting

Topic A: 0	Formatting a project file

A-1:	Modifying a bar style

A-2:	Formatting a timescale

Topic B: 0	Using drawing tools

B-1:	Using the Drawing toolbar

Topic C: 0	Printing views and reports

C-1:	Printing the current view as a report

C-2:	Printing a report

Topic D: 0	Customizing reports

D-1:	Creating a custom report

D-2:	Creating a Crosstab report

Unit 4:	Customizing the project environment

Topic A: 0	Creating custom views

A-1:	Creating a custom Network Diagram view

A-2:	Creating a combination view

Topic B: 0	Creating macros

B-1:	Creating a macro

B-2:	Running a macro

Topic C: 0	Creating a toolbar and a menu

C-1:	Creating a toolbar

C-2:	Deleting a toolbar

C-3:	Creating a new menu

C-4:	Deleting a menu

Topic D: 0	Creating a custom table

D-1:	Creating a custom table

Unit 5:	Managing multiple projects

Topic A: 0	Consolidating and sharing projects

A-1:	Consolidating project files

A-2:	Linking tasks across projects

A-3:	Assigning project and task priorities

A-4:	Making an existing filter global

A-5:	Sharing a filter between projects

Topic B: 0	Sharing resources across projects

B-1:	Sharing resources from another project

Unit 6:	Project communications

Topic A: 0	Communicating among a project team

A-1:	Discussing Microsoft Project Server 2003

A-2:	Sending task assignment requests

A-3:	Sending status requests

A-4:	Sending schedule notes

Topic B: 0	Exporting project data to the Web

B-1:	Saving the project file as a Web page

B-2:	Viewing the project file as a Web page

Topic C: 0	Working with hyperlinks

C-1:	Adding a hyperlink

Topic D: 0	Saving projects to Microsoft Project 98

D-1:	Saving a project file to Microsoft Project 98

D-2:	Identifying lost elements

Unit 7:	Exchanging project data

Topic A: 0	Importing data

A-1:	Importing data from a Microsoft Excel workbook

A-2:	Importing data from a Microsoft Access database

Topic B: 0	Exporting data

B-1:	Exporting data to a Microsoft Excel workbook

B-2:	Exporting data to a Microsoft Access database

Topic C: 0	Copying data

C-1:	Copying a Gantt chart to a Microsoft Word document

C-2:	Copying task sheet information to a Microsoft Excel worksheet